## Sheet1
Flutter Estimated Time sheet :Drabo.elitehrms.com
S.NO | MenuGroup | Screens | Screen Details | Estimated Hours | Api integration | Status
1 | Flash | FlashScreen | Image need to load | 10mins | Inprogress | Inprogress
2 | Domain | DomainScreen | Input,next,and exit button | 3 | Inprogress | Inprogress
3 | Login | LoginScreen | two input box,Forget button with email or signin valitaion,signup | 1 days
4 | Dashboard | Dashboard | Screen design and Total 6 tab design inside for every tab api integration required | 1days | Inprogress | Inprogress
5 | Personal | My profile | Total four profile information required using card design and photo changing option upload and delete photo required | 7 | Inprogress | Inprogress
6 | Personal | Other info | Total three information required using card design | 2 | Inprogress | Inprogress
7 | Personal | Address info | Total two information required using card design | 3 | Inprogress | Inprogress
8 | Personal | Education info | Card design edit,insert,update and attachment url viewing options | 7 | Inprogress | Inprogress
9 | Personal | Previous Employment | Card design edit,insert,update and attachment url viewing options | 7 | Inprogress | Inprogress
10 | Personal | Nominees Details | Card design edit,insert,update and attachment url viewing options | 7 | Inprogress | Inprogress
11 | Personal | Family details | Card design edit,insert,update. | 7 | Inprogress | Inprogress
12 | Personal | Documents | Card design edit,insert,update and attachment url viewing options | 7 | Inprogress | Inprogress
13 | Personal | Employee Skills | Card design edit,insert,update and attachment url viewing options | 7 | Inprogress | Inprogress
14 | Personal | Employee Assets | Card design edit,insert,update and attachment url viewing options | 7 | Inprogress | Inprogress
15 | Personal | Employee Award | Card design edit,insert,update and attachment url viewing options | 7 | Inprogress | Inprogress
16 | Personal | Employee VISA | Card design edit,insert,update and attachment url viewing options | 7 | Inprogress | Inprogress
17 | Personal | Leave Request | Leave Applaying ,Pending Status,Reject,history view | 1 days | Inprogress | Inprogress
18 | Personal | My Calander | need to card Design | 2 days | Inprogress | Inprogress
19 | Personal | My Training Feedback | data History view and edit and data binding screen | 7 | Inprogress | Inprogress
20 | Personal | AR Request | Card Design with four tab-controller,add and edit and delete ,status pending | 6 | Inprogress | Inprogress
21 | Personal | Payslips | Dropdown and download options | 5 | Inprogress | Inprogress
22 | Personal | Tax slips | Dropdown and download options | 4 | Inprogress | Inprogress
23 | Personal | It declaration | Total 5 tabs inserts and update,screen as more logics in details to display | 6 | Inprogress | Inprogress
24 | Personal | ORG Chart | card design | 6 | Inprogress | Inprogress
25 | Personal | YTD payview | Two row data card in type type | 3 | Inprogress | Inprogress
26 | Personal | CTC Breakup | two card | 3 | Inprogress | Inprogress
27 | Personal | Holiday Calender | piechart , four card ,holiday popup | 2 days | Inprogress | Inprogress
28 | Personal | MY resignation | one search bar ,add , data binding,dropdown,inserts data | 3 | Inprogress | Inprogress
29 | Personal | New assets Request | one search bar ,add , data binding,dropdown,inserts data | 3 | Inprogress | Inprogress
30 | Personal | Shift Changes | one search bar ,add , data binding,dropdown,inserts data | 3 | Inprogress | Inprogress
31 | Personal | Loan Request | one search bar ,add , data binding,dropdown,inserts data | 4 | Inprogress | Inprogress
32 | Personal | Compenstory off Request | one search bar ,add , data binding,dropdown,inserts data | 4 | Inprogress | Inprogress
33 | Support | Infra Request | add , insert and data bainding card | 3 | Inprogress | Inprogress
34 | Support | Policy and Document | document proof | 2 | Inprogress | Inprogress
35 | Support | ESS survey | insert , delete,pending,search,data binding,excel share | 3.5 | Inprogress | Inprogress
36 | Support | Communicator | search,add,view profile | 3 | Inprogress | Inprogress
37 | Reimbusement | LTA claim Request | date picker ,dropdown,four addachment,edit,clear,submit | 4 | Inprogress | Inprogress
38 | Reimbusement | Travel Reimbusement | date picker ,dropdown,four addachment,edit,clear,submit,excel share | 4.1 | Inprogress | Inprogress
39 | Travel Request | Travel Request | three dropdown,3 date picker,insert data,data binding,excel share | 4 | Inprogress | Inprogress
40 | Travel Request | Advance Request | three dropdown,3 date picker,insert data,data binding,excel share | 4 | Inprogress | Inprogress
41 | Travel Request | Claim Request | three dropdown,3 date picker,insert data,data binding,excel share | 4 | Inprogress | Inprogress
42 | Recruitment | Recruitment Feedback | Search ,data view or data binding | 2 | Inprogress | Inprogress
43 | My Team | on Call Entry | Search ,data view or data binding,excel Share | 2.5 | Inprogress | Inprogress
44 | ESS-Report | My Holiday | Search ,data view or data binding,excel Share | 2.5 | Inprogress | Inprogress
45 | ESS-Report | My Leave | Search ,data view or data binding,excel Share | 2.5 | Inprogress | Inprogress
46 | ESS-Report | Review Travel Reimbusement summary | Search ,data view or data binding,excel Share | 2.5 | Inprogress | Inprogress
47 | ESS-Report | Daily Attendance | Search ,data view or data binding,excel Share | 2.5 | Inprogress | Inprogress
48 | ESS-Report | employee geo punch | Search ,data view or data binding,excel Share | 2.5 | Inprogress | Inprogress
49 | ESS-Report | My Attendance | Search ,data view or data binding,excel Share | 2.5 | Inprogress | Inprogress
50 | ESS-Report | Review Assgin Policies ESS | Search ,data view or data binding,excel Share | 2.5 | Inprogress | Inprogress
51 | ESS-Report | Review ESS New Request | Search ,data view or data binding,excel Share | 2.5 | Inprogress | Inprogress
52 | ESS-Report | Review ESS services Request | Search ,data view or data binding,excel Share | 2.5 | Inprogress | Inprogress
53 | ESS-Report | Review ESS COFF Request Approval Details | Search ,data view or data binding,excel Share | 2.5 | Inprogress | Inprogress
54 | PMS | My Appraisal | Search ,dataview or data binding,create,excel Share | 3.5 | Inprogress | Inprogress
55 | PMS | DraReview Appraisal | Search ,dataview or data binding,create,excel Share | 3.5 | Inprogress | Inprogress
56 | PMS | My Goal | Search ,dataview or data binding,create,excel Share | 3.5 | Inprogress | Inprogress
57 | PMS | Self Appraisal | Search ,dataview or data binding,create,excel Share | 3.5 | Inprogress | Inprogress
58 | PMS | Review Appraisal | Search ,dataview or data binding,create,excel Share | 3.5 | Inprogress | Inprogress
59 | Over all | Language | Tamil,Hindi,Engkish | 6 | Inprogress | Inprogress
60 | Theme | UI Theme | Night Mode,Dark Mode | 6 | Inprogress | Inprogress