## Admin (hidden)
S.No | Module | Screen | Remarks
1 | Dashboard | Dashboard | Not showing any dashboard | Still same
2 | Icon | Admin Icon | It showing a screen which not having any data and any screen name | Missing
3 | Icon | Chat Icon | Showing 404 Error | Missing
4 | Icon | Leave Icon | Showing 404 Error | Showing blank, not showing anything
5 | Icon | Payroll Icon | Showing 404 Error | Showing Payroll process screen
6 | Icon | Payroll reports Icon | Showing 404 Error | Missing
7 | Icon | HR Data Icon | Showing 404 Error | Showing blank, not showing anything
8 | Icon | H2R Icon | Showing 404 Error | Showing Job offer screen
9 | Admin | Group of Company | Search data showing after 3 to 4 Seconds only | Working
10 | Admin | Group of Company | Filter - Workarea filter not allowing to type and not showing any value in Drop down, Other filters are working | Workarea filter removed
11 | Admin | Company | Search data showing after 3 to 4 Seconds only | Working
12 | Admin | Company | Filter - Workarea and Company name filter not allowing to type and not showing any value in Drop down, Company code filter is working
13 | Admin | Company | As per Mr.Dinakaran Instruction, he told that once the company is created all the settings code will load automatically, but all the settings are loaded except OnBoardStructureType settings code
14 | Admin | Screen | Search data showing after 3 to 4 Seconds only
15 | Admin | Screen | Filters are working fine
16 | Admin | Menugroup | Search data showing after 3 to 4 Seconds only
17 | Admin | Menugroup | Addition Column mentioned as Default Screen, please let me know the purpose
18 | Admin | Menugroup | Delete option not verified due to predefined
19 | Admin | Menugroup | Filters are working fine
20 | Admin | Menugroup | In excel, first report is not having menugroup id and unable to match the screen which having particular menu group
21 | Admin | Role | Search data showing after 3 to 4 Seconds only
22 | Admin | Role | Addition Check box - Audit and Import, please let me know the purpose
23 | Admin | Role | In export to excel, selected column filter is not working, selected one or two column also it export all the data's
24 | Admin | User | Search data showing after 3 to 4 Seconds only
25 | Admin | User | As of now user is common for all the company, but now even the user has all the company permission in other company users are not showing
26 | Admin | User | In Screen, it showing 3 Regular and 3 management paygroup, paygroup we need to show only for particular company not for all at a time
27 | Admin | User | While Additing new user Workarea details not showing, it showing blank
28 | Admin | User | We can able to login the user if the user status is inactive also
29 | Admin | Dashboard | Search data showing after 3 to 4 Seconds only
30 | Admin | Dashboard | SP names are not showing in search page
31 | Admin | Dashboard | Already created dashboards size and screens are missing for most of the dashboards
32 | Admin | Password Policy | Default one so not updated any entry
33 | Admin | Mailtemplate | We can able to edit, based on mail sending, so not verified others
34 | Admin | System Config | Need to give the site URL is Bo URL, but given API URL here, please explain in details
35 | Admin | Review User | In Search page, while search each record showing three three times
36 | Admin | Review User | In Excel, selected columns are not working properly
37 | Admin | Review User | While exporting one login showing multiple times

## Common (hidden)
S.No | Module | Screen | Remarks
1 | Common | Currency | Search data showing after 3 to 4 Seconds only
2 | Common | Currency | Preloaded data so not required to test
3 | Common | Currency | Filters are working
4 | Common | Country | Search data showing after 3 to 4 Seconds only
5 | Common | Country | Preloaded data so not required to test
6 | Common | Country | Filters are working
7 | Common | State | Search data showing after 3 to 4 Seconds only
8 | Common | State | While choosing view and edit icon, not showing the data, it showing the warning, sorry no data available message
9 | Common | State | Filters are working
10 | Common | Period | In search page it showing the date format as dd/mm/yyyy, in inner page it showing mm/dd/yyyy, Please change uniformly, better to change in dd/mm/yyyy format
11 | Common | Period | Search data showing after 3 to 4 Seconds only
12 | Common | Period | Filters are working
13 | Common | Period | Exporting to excel - Finacial year and leave cut off from and to date is missing
14 | Common | HR Code | Search data showing after 3 to 4 Seconds only
15 | Common | HR Code | Filters are working
16 | Common | HR Code | In Add mode, HR code column, numerix are not allowing, please allow the same, in description it allowing
17 | Common | Structure | Search data showing after 3 to 4 Seconds only
18 | Common | Structure | Filters are working
19 | Common | Bank | In Add Mode, Once state choosen need to pick the country automatically from state master, now its not working
20 | Common | Bank | In Add, While trying to add duplicate record, need to show record already exist message, instead of this now showing Insertion failed message
21 | Common | Bank | Search data showing after 3 to 4 Seconds only
22 | Common | Bank | Filters are working
23 | Common | Bank | While Exporting Excel min and max length detail is not showing
24 | Common | Location | In Add Mode, Once state choosen need to pick the country automatically from state master, now its not working
25 | Common | Location | Search data showing after 3 to 4 Seconds only
26 | Common | Location | Location Filter not Working
27 | Common | Location | While Exporting Excel need to show only location details, but now it exporting the workarea table details (including company names)
28 | Common | Connect Me | Search data showing after 3 to 4 Seconds only
29 | Common | Connect Me | In Edit mode, Land line number allow us to entry alphabates, need to allow only numbers
30 | Common | Connect Me | In LandLine number, if we update the data and save it disappered in Edit mode unable to check the landline number
31 | Common | Connect Me | In Exporting excel, it showing the field name called Date, in text format, please update in dd/mm/yyyy format also please mention what date is that?
32 | Common | Connect Me | Please remove the add option, not we can able to add the new entry, we wont allow to add here
33 | Common | Interviewer List | Search data showing after 3 to 4 Seconds only
34 | Common | Interviewer List | In Edit mode and view mode, it showing blank, not showing any data
35 | Common | Interviewer List | Add Mode also showing blank not showing any screen
36 | Common | Interviewer List | While Exporting not showing interiewer list regarding data, showing only employee details
37 | Common | Interviewer List | Filter Named as process status - Please let me know the column is related with interviewer list
38 | Common | Interviewer List | Filter - Service Position Drop down not showing any values
39 | Common | Question | In Add move, if we choose the answer type as choosen or multi choosen only, feedback answer type is mandatory, if choosen as free form feedback answer type is not mandatory, now unable to save without feedback answer type even the answer type is freeform
40 | Common | Question | While exporting excel feedback answer grid value is not showing
41 | Common | Feedback Template | Feed back template code is auto generated, but now it allow us to enter
42 | Common | Feedback Template | While exporting excel grid value is not showing
43 | Common | Survey | Survey status showing empty, unable to add the record
44 | Common | Survey | Employee search filter is used to search any one employee to add in grid, that option is not working
45 | Common | Policy Template | In Document Type, need to showing the document type list in HR Code, now it showing document hrcode value instead of document type
46 | Common | Policy Template | Not Having ESS option to check whether created data showing In ESS or not
47 | Common | Policy Template | In Inner Page date format showing as mm/dd/yyyy and in search page it showing as dd/mm/yyyy
48 | Common | Policy Template | While exporting excel grid value is not showing
49 | Common | Assign Policy | While Exporting to excel it showing only, other details are not showing
50 | Common | Infra Department | Transaction number is auto generated, Now it allowing us to update
51 | Common | Infra Department | Request type and Role need to give in grid, now we have only one save option, not having add option in grid

## HR Data (hidden)
S.No | Module | Screen | Remarks
1 | HR Data | Employee Details | Search data showing after 4 to 5 Seconds only
2 | HR Data | Employee Details | While Choosing View Option upto Skill tab save buttons are unable to found, After moving to award tab all the save and grid options are enabled, while saving the employee details it showing as exemption occurred message, while saving salary tab it showings are updated successfully message
3 | HR Data | Employee Details | State and Salutations are not mandatory, but while editing and saving the employee details it asking as mandatory, after updating also unable to save the record, it showing exemption occurred message
4 | HR Data | Employee Details | Service Position and position status must be disable, but now its open
5 | HR Data | Official | If bank name is given Bank account number and IFSC's are mandatory, but now it saving only bank name without accountnumber and IFSC
6 | HR Data | Official | In Bank Account number, While updating only Single Digit it asking to update minimum 2 digit (Account number Min and Max length digit verfication not down here
7 | HR Data | Official | In IFSC Code, While updating only Single Digit it asking to update minimum 2 digit (IFSC Code Must Consists of 11 length Combined with Alpha numeric and first 4 character must be a alphabates - Validation not donw here, please check the validations)
8 | HR Data | Official | We wont allow the duplicate bank account number for employees, not it allowing to update the same number to muliple employee - Duplicate validation not down here)
9 | HR Data | Official | WE are unable to allow the user to save the bank account number without bank name, but now it allow us to save (If paymode is neft, we wont allow to save without bank anme, account number and IFSC - Validation not down)
10 | HR Data | Official | WE are unable to allow the user to save the IFSC without bank name and account number, but now it allow us to save (If paymode is neft, we wont allow to save without bank anme, account number and IFSC - Validation not down)
11 | HR Data | Official | If the employee is probation status we wont allow the user to update the date in contract exp date and Contract month, but now its allow us to upate
12 | HR Data | Official | Confirmation date and must be auto calculated, if the probation month is given we need to auto calculate the confirmation date, but now it allow us to update
13 | HR Data | Official | Contract Exp date and must be auto calculated, if the Contract month is given we need to auto calculate the confirmation date, but now it allow us to update
14 | HR Data | Official | Employee DOJ is 01.01.2024, while updating the 31/10/2023 as confirmation date it accepting without any error
15 | HR Data | Official | Employee DOJ is 01.01.2024, while updating the 31/10/2023 as Contract Exp date it accepting without any error
16 | HR Data | Official | Auto user creation configuration not done
17 | HR Data | Official | Notice period column is missing
18 | HR Data | Personal | Relegion - Spelling Mistake - Religion - Correct
19 | HR Data | Personal | Passport Single word not Pass port
20 | HR Data | Personal | Driving License Reg No not Driving Reg no
21 | HR Data | Personal | Driving License Expiry Date not Driving Expiry date
22 | HR Data | Personal | Aadhar number field is missing - We have an mandatory settings code for this - configuration missing
23 | HR Data | Personal | GP Medicalpolicy CompanyNumber - Column Missing
24 | HR Data | Personal | GP Medical PolicyAmount - Column Missing
25 | HR Data | Education | unable to save the record, it showing please fill all the mandatory details, even after addition education details in grid
26 | HR Data | Asset | Asset Status showing 3 3 time, Draft -Times, issued 3 time all the status 3 times
27 | HR Data | Asset | unable to save the record, it showing Asset info updation failed, even after adding the asset details in Grid
28 | HR Data | Asset | We need to allow the user to save the tab without grid also, now its wont
29 | HR Data | Skill | We need to allow the user to save the tab without grid also, now its wont
30 | HR Data | Skill | In Upload file it showing You can upload only one file which should not exceed 5 MB, But now it allow us to pick more files
31 | HR Data | Skill | Unable to view the already added file
32 | HR Data | Award | If we add the data in grid and save the award of we deleted the same again and save again it again take the same grid data and saving the deleted record
33 | HR Data | Award | If we have 2 grid record, while give save without any changes it showing as 4 data ingrid, if saving again it showing 8 data so on
34 | HR Data | Address | Save and Clear button should be in buttom of the screen, now its in middle screen
35 | HR Data | Address | If we cleared and given as save it again showing the cleared data - unable to clear the saved data
36 | HR Data | Statutory | PAN number validation not done it asking to enter only minimum of 2 digit, we have some validation for PAN number
37 | HR Data | Statutory | PAN duplicate validation not done, it allow the same data for multiple employees
38 | HR Data | Statutory | In Relation ship Global Dropdown, after making the relationship as inactive also, it showing in dropdown
39 | HR Data | Statutory | PF number Duplicate validation not done, if we add the same number to another employee we wont allow, now its allow
40 | HR Data | Statutory | UAN number Duplicate validation not done, if we add the same number to another employee we wont allow, now its allow
41 | HR Data | Statutory | ESI number Duplicate validation not done, if we add the same number to another employee we wont allow, now its allow
42 | HR Data | Statutory | Once Bonus applicable only we need to allow the user to enter bonus starts date now it allow if bonus not applicable also
43 | HR Data | Statutory | Once Gratuity applicable only we need to allow the user to enter Gratuity starts date now it allow if Gratuity not applicable also
44 | HR Data | Statutory | After giving Clear and saving statutory tab, employee name also cleared from all the tabs and also from search page
45 | HR Data | Nominee | Gender - While adding into grid gender saving as code instead of name
46 | HR Data | Nominee | Unable to save the nomination without DOB it showing nomination updation failed message - but DOB not mandatory
47 | HR Data | Nominee | While adding into grid itself if we add the percentage more that 100 we wont allow to add, but now It allow, if same nominee type is given as 50% and 70% while adding we need to show the error message as PF Nominee (Nominee Type) percentage could not be exceed more than 100% but now its allowing
48 | HR Data | Nominee | If we cleared and given as save it again showing the cleared data - unable to clear the saved data
49 | HR Data | Nominee | If we deleted the grid date and given as save it again showing the deleted data
50 | HR Data | Nominee | If we have 2 grid record, while give save without any changes it showing as 4 data ingrid, if saving again it showing 8 data so on
51 | HR Data | Document | We need to allow the user to save the tab without grid also, now its wont it showing exemption occurred message
52 | HR Data | Previous Employeement | We need to allow the user to save the tab without grid also, now its wont
53 | HR Data | Previous Employeement | In Upload file it showing You can upload only one file which should not exceed 5 MB, But now it allow us to pick more files
54 | HR Data | Previous Employeement | Unable to view the already added file
55 | HR Data | Employee Details Search page | Delete option not working
56 | HR Data | Employee data | Manual creating asking the state and salutations are mandatory, but these two are not mandatory while upload master upload
57 | HR Data | Employee data | Last highest code is EIS2050, while itserting manually need to show the code as EIS2051, instead of it showing EIS0051
58 | HR Data | Master upload | Manual creating asking the state and salutations are mandatory, but these two are not mandatory while upload master upload
59 | HR Data | Master upload | Paygroup is not mandatory while manual create, but it asking as mandatory while upload
60 | HR Data | Master Update | While update employee code and name only mandatory, but system asking Rowno : 2,column name : DateOfJoining : DateOfJoining Cannot Be Empty Rowno : 2,column name : Gender : Gender Cannot Be Empty Rowno : 2,column name : GlobalLocation : GlobalLocation Cannot Be Empty Rowno : 2,column name : PossitionStatus : PossitionStatus Cannot Be Empty Rowno : 2,column name : ServicePosition : ServicePosition Cannot Be Empty Rowno : 2,column name : DOB : DOB Cannot Be Empty Rowno : 2,column name : PayGroup : PayGroup Cannot Be Empty
61 | HR Data | Master Update | While update paymode as neft bank name, account number and IFSC is mandatory now its not showing in error
62 | HR Data | Geo Fencing | Only screen design completed
Note | All the duplicate validations are only for live employees not resigned

## H2R (hidden)
S.No | Module | Screen | Remarks
1 | H2R | Job Offer | Search data showing after 4 to 5 Seconds only
2 | H2R | Job Offer | In Referal dropdown, if we disabled some dropdown option using Global dropdown also, it wont work
3 | H2R | Job Offer | Vacancy Position showing empty
4 | H2R | Job Offer | In Salutation dropdown, if we disabled some dropdown option using Global dropdown also, it wont work
5 | H2R | Job Offer | In Gender dropdown, if we disabled some dropdown option using Global dropdown also, it wont work
6 | H2R | Job Offer | In Service Position dropdown, if we disabled some dropdown option using Global dropdown also, it wont work
7 | H2R | Job Offer | In Position status dropdown, if we disabled some dropdown option using Global dropdown also, it wont work
8 | H2R | Job Offer | In Pay structure dropdown, if we disabled some dropdown option using Global dropdown also, it wont work
9 | H2R | Job Offer | Unable to generate the letter
10 | H2R | Job Offer | In Export to excel payelement values are not showing
11 | H2R | Job Offer | Once Joined, we wont allow to make changes, but now we can.
12 | H2R | Applicant induction | Once given has joined user created without Role
13 | H2R | Applicant induction | Unable to generate the letter
14 | H2R | Applicant induction | In Export to excel payelement values are not showing
15 | H2R | Applicant induction | Once Joined, we wont allow to make changes, but now we can.
16 | H2R | Applicant induction | Their no structure named as unit (Unit is division) its updated for Faber we need to show our base details, it showing in filter
17 | H2R | Increment | While entrying increment increment details are not showing, unable to enter the increment details
18 | H2R | Increment | Salary revision date accepting the payroll not processed date also, we are unable to enter the increment for payroll not processed date, here we need to calculcate the arrear from the period
19 | H2R | Increment | In Transaction status dropdown, if we disabled some dropdown option using Global dropdown also, it wont work
20 | H2R | Increment | Unable to generate the letter
21 | H2R | Increment | Once finalized, we wont allow to make changes, but now we can, we can change the status again to draft
22 | H2R | Increment | Their no structure named as mode of business and unit (Unit is division and mode of business is subdepartment) its updated for Faber we need to show our base details, it showing in filter
23 | H2R | Promotion | While entrying Promotion, role dropdown showin the struture role details, in edit mode it showing the user role details
24 | H2R | Promotion | Once finalized, we need to update the new structure values in to employee details table, but now its not updating
25 | H2R | Promotion | Once finalized, in edit mode it showing only one record in grid other records are not showing
26 | H2R | Promotion | Unable to find the generate letter button
27 | H2R | Promotion | In Exporting Excel grid details are not showing
28 | H2R | Promotion | Once finalized, we wont allow to make changes, but now we can, we can change the status again to draft
29 | H2R | Promotion | We wont allow the promation data as past date, but now it allow
30 | H2R | Promotion | We wont allow the save without chaning any one of the grid new position, but now it allow us to save
31 | H2R | Promotion | Their no structure named as mode of business and unit (Unit is division and mode of business is subdepartment) its updated for Faber we need to show our base details, it showing in filter
32 | H2R | Location Transfer | Search data showing after 4 to 5 Seconds only
33 | H2R | Location Transfer | In Transaction status dropdown, if we disabled some dropdown option using Global dropdown also, it wont work
34 | H2R | Location Transfer | In Exporting Excel it showing grid header, but here not grids available
35 | H2R | Location Transfer | Once finalized, we need to update the new Loaction values in to employee details table, but now its not updating
36 | H2R | Location Transfer | Once finalized, we wont allow to make changes, but now we can, we can change the status again to draft
37 | H2R | Location Transfer | Unable to find the generate letter button
38 | H2R | Location Transfer | Their no structure named as mode of business and unit (Unit is division and mode of business is subdepartment) its updated for Faber we need to show our base details, it showing in filter
39 | H2R | Separation | In Reliving type dropdown, if we disabled some dropdown option using Global dropdown also, it wont work
40 | H2R | Separation | In Separation type dropdown,no data showing in Global dropdown, but values showing in dropdown
41 | H2R | Separation | Search data showing after 4 to 5 Seconds only
42 | H2R | Separation | Once separation entry updated as resigned need to update the employee status as resigned, but now no changes in employee position status
43 | H2R | Separation | Once separation entry updated as resigned need to update the user status as inactive, but now no changes in user status
44 | H2R | Separation | Once Separation entry has been deleted, we need to change the employee position status as old status, but now we are not chaning the status while separation, so we are unable to check this point
45 | H2R | Separation | Reason for Reliving and Reason type field is missing in screen
46 | H2R | Separation | In Report, reliving type showing as reliving name and separation type showing as separation name
47 | H2R | Separation | In Report code showing as wrong name and employee code showing in mid of the report
48 | H2R | Separation | In Report Reason for Reliving and Reason type column showing but not in screen, reason type showing as reliving type
49 | H2R | Separation | On column showing as leave type name, not related with separation
50 | H2R | Separation | Only acceptance and experience letter buttons are available unable to find the reliving letter button, letter also not generated
51 | H2R | Separation | Their no structure named as mode of business and unit (Unit is division and mode of business is subdepartment) its updated for Faber we need to show our base details, it showing in filter
52 | H2R | Separation | Separation type filter showing the position status dropdown value
53 | H2R | Intra Transfer | Search data showing after 4 to 5 Seconds only
54 | H2R | Intra Transfer | While Saving Transaction date given as 01/05/2024, but it automatically changed as 02/01/1990 after saving
55 | H2R | Intra Transfer | In Transaction status dropdown, if we disabled some dropdown option using Global dropdown also, it wont work
56 | H2R | Intra Transfer | Once finalized, new structure values are removed
57 | H2R | Intra Transfer | Once finalized, we need to update the new structure values in to employee details table, but now its removing from intra transfer
58 | H2R | Intra Transfer | In Export, Grid detail showing blank and also once more additional grid showing which is not related to that report
59 | H2R | Intra Transfer | Their no structure named as mode of business and unit (Unit is division and mode of business is subdepartment) its updated for Faber we need to show our base details, it showing in filter
60 | H2R | CCC Extension | Search data showing after 4 to 5 Seconds only
61 | H2R | CCC Extension | Their no structure named as mode of business and unit (Unit is division and mode of business is subdepartment) its updated for Faber we need to show our base details, it showing in filter
62 | H2R | CCC Extension | There is no Transfer revision date in CCC exten screen, but showing the filter in this name
63 | H2R | CCC Extension | While Saving New REvision date given as 01/05/2024, but it automatically changed as 02/01/1990 after saving
64 | H2R | CCC Extension | In Transaction status dropdown, if we disabled some dropdown option using Global dropdown also, it wont work
65 | H2R | CCC Extension | Probation externed, button not showing any values
66 | H2R | CCC Extension | Letter generation not working
67 | H2R | CCC Extension | Once finalized, we need to change the employee position status in Employee db table, not its not changed
68 | H2R | CCC Extension | Once finalized, we cant able to make any changes, but not its allow us to make changes
69 | H2R | CCC Extension | In Exporting Excel it showing grid header, but here not grids available
70 | H2R | CCC Extension | In Report Employee code and Name filter showing 2 times
Note | All the screen date format showing as mm/dd/yyyy, instead of dd/mm/yyyy

## Leave (hidden)
S.No | Module | Screen | Remarks
1 | Leave | Holiday Calender | While choosing date if the date is not in selected period need to show the error as Selected date is not in selected period, please check, but now its not checking the date it in selected period or not
2 | Leave | Holiday Calender | Search data showing after 4 to 5 Seconds only
3 | Leave | Holiday Planner | Search data showing after 4 to 5 Seconds only
4 | Leave | Holiday Planner | If we save without selecting Holidays need to show the error as Please select Holidays, but now its accepting without selecting holiday also
5 | Leave | Holiday Planner | In Exporting Excel, Unable to see the holiday lists, Holiday list grid is empty
6 | Leave | Holiday Planner | Delete button is not performing, unable to delete
7 | Leave | Holiday Planner | Wont allow the Holiday planner in duplicate name, now its allowing duplicate holiday planner name
8 | Leave | Leave Process | Unable to get the grid data while processing, but downloaded the leave process data in leave process upload screen for the period for May 24 in management payroll, but not showing the data Leave process screen
9 | Leave | Leave Adjustment | Leave type filter need to load only leave filter checked leave types, now it showing all the leave types
10 | Leave | Leave Balance Upload | Leave type need to allow only leave filter checked leave types, now it showing all the leave types
11 | Leave | Leave Credit Policy | Unable to check the screen, all the dropdowns are empty
12 | Leave | Leave Credit Policy | Screen name is not showing
13 | Leave | Leave Taken Policy | Screen name is not showing
14 | Leave | Leave Taken Policy | In Stoke it showing the payelement name instead of stoke name
15 | Leave | Leave Taken Policy | Total number of days showing leave taken policy name, unable to enter the day details, once we earsed, leave taken policy name also erased
16 | Leave | Leave Taken Policy | Day Span loading payelement name instead of day span
17 | Leave | Leave Taken Policy | Custom rule loading payelement name instead of custom rule dropdown
18 | Leave | Leave Taken Policy | Unable to check the screen, all the dropdowns are incorrect
19 | Leave | Leave Policy | Unable to check the screen, because of leave credit and taken policys are empty
20 | Leave | Leave Policy | We have two leave policy screen, now we have only one

## Payroll (hidden)
S.No | Module | Screen | Remarks
1 | Payroll | Payelement | Search data showing after 4 to 5 Seconds only
2 | Payroll | Payelement | In element type Global Dropdown, after making the some data's as inactive also, it showing in dropdown
3 | Payroll | Payelement | In element method Global Dropdown, after making the some data's as inactive also, it showing in dropdown
4 | Payroll | Payelement | In Benefit Period Global Dropdown, after making the some data's as inactive also, it showing in dropdown
5 | Payroll | Payelement | In Exporting excel, it showing the grid header 2 times which is not required
6 | Payroll | Payelement | In Payelement type, payelement method and element nature need to show the names, now it showing ID
7 | Payroll | Payelement | In Report Paygroup column not required
8 | Payroll | Payelement | In Report instead of True or false, need to show yes or no for flag details
9 | Payroll | Payelement | Custom1, 2 and 3 are not showing in report
10 | Payroll | Rule bulider | Search data showing after 4 to 5 Seconds only
11 | Payroll | Rule bulider | In Exporting excel, it showing the grid header 2 times which is not required
12 | Payroll | Rule bulider | Exporting Excel report in incorrect order
13 | Payroll | Rule bulider | In Arrear Maaping, element mapping need to show the names, now it showing ID
14 | Payroll | Rule bulider | Paygroup ID,RuleAreaElementType, Rule type,Extendardsecion,ExtendardRulearea, RulePriorityName columns not required
15 | Payroll | Rule bulider | Round off column showing two times
16 | Payroll | Rule bulider | In Map element Global Dropdown, after making the some data's as inactive also, it showing in dropdown
17 | Payroll | Rule bulider | In rule type Global Dropdown, after making the some data's as inactive also, it showing in dropdown
18 | Payroll | Rule bulider | In Round off Global Dropdown, after making the some data's as inactive also, it showing in dropdown
19 | Payroll | Rule bulider | In Earning And Deduction, Earnings and dedcution column are overlapped
20 | Payroll | Rule bulider | Unable to clear the selected number alone, while choosing clear in number box, it cleared all the rules
21 | Payroll | Rule bulider | If the rule type as direct we wont allow to enter the data in Rule area, now its allowing
22 | Payroll | Statutory Builder | While saving the record it showing updating failed, but entry inserted
23 | Payroll | Statutory Builder | Search data showing after 4 to 5 Seconds only
24 | Payroll | Statutory Builder | In screen Company name Dropdown it showing only current company, but in filter It showing all the companies
25 | Payroll | Statutory Builder | While inserting I have choosed only Company name, but in edit mode it showing PT_LWF_ComissonerDetails grid with values, if we delete and inserted again, grid details showing 2 times
26 | Payroll | Statutory Builder | Report is not necessary, it showing unwanted columns
27 | Payroll | PT | In Payroll type Global Dropdown, after making the some data's as inactive also, it showing in dropdown
28 | Payroll | PT | Unable to find the PT Value grid to check the screen, PT grid details are not available
29 | Payroll | PT | After saving value will be inserted in statutory builder screen, now we are unable to check this point
30 | Payroll | Payslip Designer | While choosing the screen it showing exemption occurred message
31 | Payroll | Payslip Designer | Master and Payelement fields are not showing to create
32 | Payroll | Payslip Designer | Spelling, Payslip not pay slip in both search page and screen
33 | Payroll | Payslip Designer | Report is not necessary, it showing unwanted columns
34 | Payroll | Payslip Designer | We can able to perform save in view mode also
35 | Payroll | Monthly input | Please let me know the purpose of select all and check boxes
36 | Payroll | Monthly input | Search data showing after 4 to 5 Seconds only
37 | Payroll | Monthly input | In Transaction status Global Dropdown, after making the some data's as inactive also, it showing in dropdown
38 | Payroll | Monthly input | In Export to excel it showing only paygroup name period and status, in that status and paygroup showing code instead of name, date format is mismatched, report not required
39 | Payroll | Monthly input | We wont allow to delete monthly input once payroll is created against that period and paygroup, now it allow us to delete
40 | Payroll | Monthly input uplaod | while choosing the screen first time all the dropdowns are empty, it takes 4 to 5 sec loading time for dropdown
41 | Payroll | Monthly input uplaod | While downloading template, if we already created the monthly input against the selected period and paygroup, we need to show the already updated data also in downloaded excel, now it showing all the value as 0, if we already done the monthly input for one 5 employee but totally we have 10 employee against that paygroup, we need to download the already created data, while first time only we need to show the fresh data, for 1st time that template is ok, once that is already created, we need to download only already created data not fresh one
42 | Payroll | Monthly input uplaod | In upload error it showing the one error in multiple time
43 | Payroll | Payelement Upload | while choosing the screen first time all the dropdowns are empty, it takes 4 to 5 sec loading time for dropdown
44 | Payroll | Payelement Upload | While downloading template, if we already uploaded the salary against the paygroup, we need to show the already updated data also in downloaded excel, now it showing all the value as 0, we need to download the already created data, while first time (New Employee) only we need to show the fresh data, for 1st time that template is ok, once that is already updated, we need to download only already updated data not fresh one
45 | Payroll | Payelement Upload | Date need to show in dd/mm/yyyy format
46 | Payroll | LWF | Unable to find the LWF Value grid to check the screen, LWF grid details are not available
47 | Payroll | LWF | After saving value will be inserted in statutory builder screen, now we are unable to check this point
48 | Payroll | Paygroup Master | After saving the data unable to view the added data in search page
49 | Payroll | Paygroup Master | In both filter in showing data picker instead of dropdown
50 | Payroll | Paygroup Master | In Exporting Excel, it showing all the company data, Waid restiction not done
51 | Payroll | Paygroup Master | Need to know the Reason of Regular, Settlement and FMS dogle button
52 | Payroll | Payroll Process | We can able to add multiple record against the same period and paygroup
53 | Payroll | Payroll Process | Auto PT Deduction is not able to check, due to entry not updated in statutory bulider report
54 | Payroll | Payroll Process | Auto LWF Deduction is not able to check, due to entry not updated in statutory bulider report
55 | Payroll | Grade Pay FMS | Paygroup is mandatory, now we are able to save without paygroup also, If we save without paygroup it showing inserted successfully message but not showing in grid
56 | Payroll | Grade Pay FMS | If the Monthly input FMS settings code is yes wont allow the user to change the grade in employee details, not grade dropdown is open, in this
57 | Payroll | Grade Pay FMS | We wont Allow the Dupliate grade, not it allows the duplicate grade, we can able to add multiple time
58 | Payroll | Grade Pay FMS | Once Grade name is created, we wont allow the user to make changes in grade name, but now it allow us to make chages
59 | Payroll | Grade Pay FMS | Once Created Grade is mapped with Employee, we wont allow to delete the record, but it allow us to delete
60 | Payroll | Monthly input upload FMS | Single Errorlog writing multiple time
61 | Payroll | Monthly input upload FMS | If we uploaded the data successfully at one time, in monthly input FMS it created two time
62 | Payroll | Monthly input upload FMS | If we uploaded the file second time, in monthly input FMS it created four times, need to change the already available value but now it inserting multiple time
63 | Payroll | Month input FMS | In Edit mode we need to check the uploaded value, but now we cant able to check, it showing sorry no data available message
64 | Payroll | Month input FMS | uploaded the employee with different grade but virtual code is not created
65 | Payroll | Month input FMS | after uploading Paygroup is not showing in monthly input FMS, Paygroup showing blank, even it has mapped in upload option
66 | Payroll | Month input FMS | We are unable to map the paygroup manually
67 | Payroll | Month input FMS | Create option is not working, we are unable to find the process option in available
68 | Payroll | Payroll Process FMS | Unable to check because of paygroup not mapped in monthly input FMS
69 | Payroll | FMS Data Posting | Unable to check because of paygroup not mapped in monthly input FMS
70 | Payroll | Single Employee Payroll Process | PostSingleEmpPayrollprocess Updation Failed error showing while process, Message need to change
71 | Payroll | Payroll Settlements | In Employee Code Dropdown, need to show only resigned employee, but now it showing all the employees
72 | Payroll | Payroll Settlements | In Period Dropdown, need to load only monthly period type period now it showing all the periods
73 | Payroll | Payroll Settlements | In that we need to give only paid days or absorbed days, only one data we need to fill, if we fill only paid days, it asking to update the absorbed days
74 | Payroll | Payroll Settlements | While inserting Settlement one time values are not showing in screen
75 | Payroll | Payroll Settlements | While inserting the settlement for live employee it showing PostPayrollsettlement Successfully message but data not showing in Search page
76 | Payroll | Payroll Settlements | While inserting the settlement for resigned employee it showing PostPayrollsettlement Successfully message but data not showing in Search page
77 | Payroll | Payroll Settlements | Success message need to change
78 | Payroll | Payroll Settlements | Unable to check filter and report, because of unable to insert the data
79 | Payroll | Loan Entry | In Screen need to change the date format as dd/mm/yyyy
80 | Payroll | Loan Entry | Loan Effective date need to update now given as month
81 | Payroll | Loan Entry | Transaction status global dropdown is not working
82 | Payroll | Loan Entry | After updating the loan Value and EMI, need to calculate the Interest amount, total loan amount, loan per month and out standing amount automatically, now its not working
83 | Payroll | Loan Entry | Unable to save the entry while saving it showing Exception Occurred message
84 | Payroll | Review Grade pay | All the filters are showing as Date picker instead of Dropdown
85 | Payroll | Review Grade pay | In export to PDF, first page showing as blank and Columns are not in order and payelement values also not showing
86 | Payroll | Review Grade pay | Select Column option is not working if we select one or 2 columns also it downloading all the columns
87 | Payroll | Review Grade pay | In export in excel, Columns are not in order and payelement values also not showing
88 | Payroll | Review Monthly Input FMS | Status filter dropdown is showing wrong data's
89 | Payroll | Review Monthly Input FMS | unable to check the export to excel because of no record showing in this screen, even we have FMS monthly input
90 | Payroll | Review Paysheet FMS | All the filters are showing as Date picker instead of Dropdown
91 | Payroll | Review Paysheet FMS | unable to check the export to excel because of no record showing in this screen
92 | Payroll | Review Pay Master | Select Column option is not working if we select one or 2 columns also it downloading all the columns
93 | Payroll | Review Pay Master | In export to PDF, first page showing as blank
94 | Payroll | Review Pay Master | In both PDF and Excel it showing the Workarea ID instead of name
95 | Payroll | Review Rule Builder | Select Column option is not working if we select one or 2 columns also it downloading all the columns
96 | Payroll | Review Rule Builder | In export to PDF, first page showing as blank
97 | Payroll | Review Rule Builder | In both PDF and Excel it showing the Workarea ID instead of name
98 | Payroll | Review Monthly Input | Select Column is not showing the column names
99 | Payroll | Review Monthly Input | In search page it totally showing 1275 records but in excel it showing only 50 records
100 | Payroll | Review Monthly Input | In both PDF and Excel it showing the Workarea ID instead of name
101 | Payroll | Review Payroll | Select Column option is not working if we select one or 2 columns also it downloading all the columns
102 | Payroll | Review Payroll | In export to PDF, first page showing as blank
103 | Payroll | Review Payroll | In both PDF and Excel it showing the Workarea ID instead of name
104 | Payroll | PF ECR | While choosing PF ECR Application gets logged out automatically
105 | Payroll | Review Employee PT | Select Column is not showing the column names
106 | Payroll | Review Employee PT | In export to PDF, first page showing as blank
107 | Payroll | Review Employee PT | In both PDF and Excel it showing the Workarea ID instead of name
108 | Payroll | Review_NAPSKAG | unable to check the export to excel because of no record showing in this screen

## OPMS (hidden)
S.No | Module | Screen | Remarks
1 | Payroll Reports | Review Payroll by employee | Export PDF showing upto DOB record, not showing Payroll details
2 | Payroll Reports | Review Payroll by employee | Select Column option is not working, not showing the column name to select
3 | Payroll Reports | Review Payroll by employee | Group by filter is not working
4 | Payroll Reports | Payroll Reconcilation | Filter name Unit and mode of business need to be change as per base application
5 | Payroll Reports | Payroll Reconcilation | Select Column option is not working, not showing the column name to select
6 | Payroll Reports | Payroll Reconcilation | Export PDF is not required
7 | Payroll Reports | Payroll Reconcilation | Unable to generate the report due to data not available
8 | Payroll Reports | Review Annual Summary | Filter name Unit and mode of business need to be change as per base application
9 | Payroll Reports | Review Annual Summary | Select Column option is not working, not showing the column name to select
10 | Payroll Reports | Review Annual Summary | Export PDF is not required
11 | Payroll Reports | Review Annual Summary | Group by filter is not working
12 | Payroll Reports | Review Annual Summary | In Excel Filter, Paygroup showing ID instead of name
13 | Payroll Reports | Review Annual Summary | In Excel Filter, Employee code showing ID instead of name
14 | Payroll Reports | Review Annual Summary | In Excel Filter, WAID showing ID instead of name
15 | Payroll Reports | Review Payroll by employee | Filter name Unit and mode of business need to be change as per base application
16 | Payroll Reports | Review Payroll by employee | In Excel Filter, Paygroup and Workarea showing ID instead of name
17 | Payroll Reports | ESIC ECR | Select Column option is not working, not showing the column name to select
18 | Payroll Reports | ESIC ECR | Export PDF is not required
19 | Payroll Reports | ESIC ECR | Excel not downloaded for already payroll processed month
20 | Payroll Reports | ESIC ECR | PDF not required, instead of PDF Required CSV format
21 | Payroll Reports | Dynamic Payslip | Select Column option is not working, not showing the column name to select
22 | Payroll Reports | Dynamic Payslip | Export PDF is not required
23 | Payroll Reports | Dynamic Payslip | Export Excel is not required
24 | Payroll Reports | Dynamic Payslip | While choosing Print Payslip not downloaded
25 | Payroll Reports | Dynamic Payslip | Send email option missing
26 | Payroll Reports | Dynamic Payslip | Option type and dropdown type - Filter Requirements Please?
27 | Payroll Reports | Dynamic Payslip | Filter name Unit need to be change as per base application
28 | Payroll Reports | Review PF ECR Revised | Select Column option is not working, not showing the column name to select
29 | Payroll Reports | Review PF ECR Revised | Export PDF is not required
30 | Payroll Reports | Review PF ECR Revised | Excel not downloaded for already payroll processed month
31 | Payroll Reports | Review PF ECR Revised | PDF not required, instead of PDF Required CSV format
32 | Payroll Reports | Review PF ECR Revised | Print Option not required
33 | Payroll Reports | Review PF ECR Revised | Filter name Unit and mode of business need to be change as per base application
34 | Payroll Reports | Gratuity Calculation | Filter name Unit and mode of business need to be change as per base application
35 | Payroll Reports | Gratuity Calculation | Service Position dropdown empty
36 | Payroll Reports | Gratuity Calculation | While choosing it showing Gratuity Calculation is not done properly. Please check
37 | Payroll Reports | Gratuity Calculation | Select Column option is not working, not showing the column name to select
38 | Payroll Reports | Gratuity Calculation | Export PDF is not required
39 | Payroll Reports | Gratuity Calculation | Print Option not required
40 | Payroll Reports | Gratuity Calculation | Unable to generate the report due to data not available
41 | Payroll Reports | Review PF UAN Generation | While choosing the screen, application gets logged out automatically
42 | Payroll Reports | Monthly Pay sheet | Configuration not done, unable to download
43 | Payroll Reports | Monthly Pay sheet | Filter name Unit and mode of business need to be change as per base application
44 | Payroll Reports | Monthly Pay sheet | Service Position dropdown empty
45 | Payroll Reports | Monthly Pay sheet | Select Column option is not working, not showing the column name to select
46 | Payroll Reports | Monthly Pay sheet | Export PDF is not required
47 | Payroll Reports | Review Professional Tax | Select Column option is not working, not showing the column name to select
48 | Payroll Reports | Review Professional Tax | Export PDF is not required
49 | Payroll Reports | Review Loan Balance DRA | Configuration not done, unable to download
50 | Payroll Reports | Review Loan Balance DRA | Export PDF is not required
51 | Payroll Reports | Review Loan Balance DRA | Print Option not required
52 | Payroll Reports | Review Loan Balance DRA | Select Column option is not working, not showing the column name to select
53 | Payroll Reports | Gratuity Report | Export PDF is not required
54 | Payroll Reports | Gratuity Report | Employee Name Filter not working
55 | Payroll Reports | Gratuity Report | Select Column option is not working, not showing the column name to select
56 | Payroll Reports | Gratuity Report | Report Details not clear, please explain
57 | Payroll Reports | Review Salary Reconciliation | Select Column option is not working, not showing the column name to select
58 | Payroll Reports | Review Salary Reconciliation | Export PDF is not required
59 | Payroll Reports | Review Salary Reconciliation | Unable to generate the report due to data not available

## Admin_New
S.No | Module | Screen | Remarks | New Remarks
1 | Dashboard | Dashboard | Not showing any dashboard | Still same issue
2 | Icon | Admin Icon | It showing a screen which not having any data and any screen name | Missing
3 | Icon | Chat Icon | Showing 404 Error | Missing
4 | Icon | Leave Icon | Showing 404 Error | Showing blank, not showing anything
5 | Icon | Payroll Icon | Showing 404 Error | Showing Payroll process screen
6 | Icon | Payroll reports Icon | Showing 404 Error | Missing
7 | Icon | HR Data Icon | Showing 404 Error | Showing blank, not showing anything
8 | Icon | H2R Icon | Showing 404 Error | Showing Job offer screen
9 | Admin | Group of Company | Search data showing after 3 to 4 Seconds only | Working
10 | Admin | Group of Company | Filter - Workarea filter not allowing to type and not showing any value in Drop down, Other filters are working | Workarea filter removed
11 | Admin | Company | Search data showing after 3 to 4 Seconds only | Working
12 | Admin | Company | Filter - Workarea and Company name filter not allowing to type and not showing any value in Drop down, Company code filter is working | Workarea filter removed, Company code filter showing same value two times
| Admin | Company | In Company creation Work Area Type global dropdown is not working | NEW
13 | Admin | Company | As per Mr.Dinakaran Instruction, he told that once the company is created all the settings code will load automatically, but all the settings are loaded except OnBoardStructureType settings code | Still same issue
| Admin | Company | Company Code - Allowing to insert duplicate | NEW
14 | Admin | Screen | Search data showing after 3 to 4 Seconds only | Working
16 | Admin | Menugroup | Search data showing after 3 to 4 Seconds only | Working
17 | Admin | Menugroup | Addition Column mentioned as Default Screen, please let me know the purpose | Explanation not given
18 | Admin | Menugroup | Delete option not verified due to predefined | Unable to check
19 | Admin | Menugroup | Filters are working fine | Working
20 | Admin | Menugroup | In excel, first report is not having menugroup id and unable to match the screen which having particular menu group | Now Export to excel option is not working, while choosing it says Exception Occurred message
21 | Admin | Role | Search data showing after 3 to 4 Seconds only | Working
22 | Admin | Role | Addition Check box - Audit and Import, please let me know the purpose | Explanation not given
23 | Admin | Role | In export to excel, selected column filter is not working, selected one or two column also it export all the data's | Now Export to excel option is not working, while choosing it says Exception Occurred message
24 | Admin | User | Search data showing after 3 to 4 Seconds only | Working
25 | Admin | User | As of now user is common for all the company, but now even the user has all the company permission in other company users are not showing | Still same issue
26 | Admin | User | In Screen, it showing 3 Regular and 3 management paygroup, paygroup we need to show only for particular company not for all at a time | Still same issue
27 | Admin | User | While Additing new user Workarea details not showing, it showing blank | Working
| Admin | User | In User creation user Type global dropdown is not working | NEW
28 | Admin | User | We can able to login the user if the user status is inactive also | Now working but showing error as invaild email address and password instead of user inactive
29 | Admin | Dashboard | Search data showing after 3 to 4 Seconds only | Working
30 | Admin | Dashboard | SP names are not showing in search page | Working
31 | Admin | Dashboard | Already created dashboards size and screens are missing for most of the dashboards | Still same issue
32 | Admin | Password Policy | Default one so not updated any entry | -
33 | Admin | Mailtemplate | We can able to edit, based on mail sending, so not verified others | -
34 | Admin | System Config | Need to give the site URL is Bo URL, but given API URL here, please explain in details | In system config it showing some other URL (FI), but still application working, please explain the process
35 | Admin | Review User | In Search page, while search each record showing three three times | Unable to check the screen loading for more than 5 min
36 | Admin | Review User | In Excel, selected columns are not working properly | Unable to check the screen loading for more than 5 min
37 | Admin | Review User | While exporting one login showing multiple times | Unable to check the screen loading for more than 5 min
| Admin | Screen field |  | Please explain

## Common_New
S.No | Module | Screen | Remarks | Remarks_New
1 | Common | Currency | Search data showing after 3 to 4 Seconds only | Working
2 | Common | Currency | Preloaded data so not required to test | -
3 | Common | Currency | Filters are working | -
4 | Common | Country | Search data showing after 3 to 4 Seconds only | Working
5 | Common | Country | Preloaded data so not required to test | -
6 | Common | Country | Filters are working | -
7 | Common | State | Search data showing after 3 to 4 Seconds only | Working
8 | Common | State | While choosing view and edit icon, not showing the data, it showing the warning, sorry no data available message | Working
9 | Common | State | Filters are working | -
10 | Common | Period | In search page it showing the date format as dd/mm/yyyy, in inner page it showing mm/dd/yyyy, Please change uniformly, better to change in dd/mm/yyyy format | Working
11 | Common | Period | Search data showing after 3 to 4 Seconds only | Working
12 | Common | Period | Filters are working | -
13 | Common | Period | Exporting to excel - Finacial year and leave cut off from and to date is missing | Exporting to excel - Finacial year is missing
14 | Common | HR Code | Search data showing after 3 to 4 Seconds only | Working
15 | Common | HR Code | Filters are working | -
16 | Common | HR Code | In Add mode, HR code column, numerix are not allowing, please allow the same, in description it allowing | Working
| Common | HR Code | In Description, we are unable to save with one character | NEW
17 | Common | Structure | Search data showing after 3 to 4 Seconds only | Working
18 | Common | Structure | Filters are working | -
19 | Common | Bank | In Add Mode, Once state choosen need to pick the country automatically from state master, now its not working | Working
20 | Common | Bank | In Add, While trying to add duplicate record, need to show record already exist message, instead of this now showing Insertion failed message | Working
21 | Common | Bank | Search data showing after 3 to 4 Seconds only | Working
22 | Common | Bank | Filters are working | -
23 | Common | Bank | While Exporting Excel min and max length detail is not showing | Working
24 | Common | Location | In Add Mode, Once state choosen need to pick the country automatically from state master, now its not working | Working
25 | Common | Location | Search data showing after 3 to 4 Seconds only | Working
26 | Common | Location | Location Filter not Working | Working
27 | Common | Location | While Exporting Excel need to show only location details, but now it exporting the workarea table details (including company names) | Working
28 | Common | Connect Me | Search data showing after 3 to 4 Seconds only | Working
29 | Common | Connect Me | In Edit mode, Land line number allow us to entry alphabates, need to allow only numbers | Working
30 | Common | Connect Me | In LandLine number, if we update the data and save it disappered in Edit mode unable to check the landline number | Working
31 | Common | Connect Me | In Exporting excel, it showing the field name called Date, in text format, please update in dd/mm/yyyy format also please mention what date is that? | Date field is removed now, but landline number is missing
32 | Common | Connect Me | Please remove the add option, not we can able to add the new entry, we wont allow to add here | Still issue exist
33 | Common | Interviewer List | Search data showing after 3 to 4 Seconds only | Working
34 | Common | Interviewer List | In Edit mode and view mode, it showing blank, not showing any data | Still issue exist
35 | Common | Interviewer List | Add Mode also showing blank not showing any screen | Still issue exist, Add mode is not required
36 | Common | Interviewer List | While Exporting not showing interiewer list regarding data, showing only employee details | Still issue exist
37 | Common | Interviewer List | Filter Named as process status - Please let me know the column is related with interviewer list | Still issue exist
38 | Common | Interviewer List | Filter - Service Position Drop down not showing any values | Working
39 | Common | Question | In Add move, if we choose the answer type as choosen or multi choosen only, feedback answer type is mandatory, if choosen as free form feedback answer type is not mandatory, now unable to save without feedback answer type even the answer type is freeform | Working
40 | Common | Question | While exporting excel feedback answer grid value is not showing | Report not clear Show the both master and grid in same column, now report is showing separately
| Common | Question | We wont allow the duplicate record, now its allow | NEW
41 | Common | Feedback Template | Feed back template code is auto generated, but now it allow us to enter | Working
42 | Common | Feedback Template | While exporting excel grid value is not showing | Still issue exist
| Common | Feedback Template | It Allow us to save the entry without grid, grid is mandatory | NEW
| Common | Feedback Template | Allow to save with duplicate template name | NEW
43 | Common | Survey | Survey status showing empty, unable to add the record | While trying to save it showing survey creation updation failed message, unable to save
44 | Common | Survey | Employee search filter is used to search any one employee to add in grid, that option is not working | Still issue exist
| Common | Survey | Now Allow us to update the to date is lesser than from date, we wont allow to enter the to date is less than from date | NEW
45 | Common | Policy Template | In Document Type, need to showing the document type list in HR Code, now it showing document hrcode value instead of document type | Still issue exist
46 | Common | Policy Template | Not Having ESS option to check whether created data showing In ESS or not | still ESS not available
47 | Common | Policy Template | In Inner Page date format showing as mm/dd/yyyy and in search page it showing as dd/mm/yyyy | Working
48 | Common | Policy Template | While exporting excel grid value is not showing | Report not clear Show the both master and grid in same column, now report is showing separately
| Common | Policy Template | Now Allow us to update the to date is lesser than from date, we wont allow to enter the to date is less than from date | NEW
49 | Common | Assign Policy | While Exporting to excel it showing only, other details are not showing | Report not clear Show the both master and grid in same column, now report is showing separately
|  | Assign Policy | While Adding it showing created successfully, but record not inserted, After choosing Location only it saving the record, but location is not given as mandatory | NEW
50 | Common | Infra Department | Transaction number is auto generated, Now it allowing us to update | Working
51 | Common | Infra Department | Request type and Role need to give in grid, now we have only one save option, not having add option in grid | Working
| Common | Infra Department | Report not clear Show the both master and grid in same column, now report is showing separately | NEW

## HR Data_New
S.No | Module | Screen | Remarks | Remarks_New
1 | HR Data | Employee Details | Search data showing after 4 to 5 Seconds only | Working
2 | HR Data | Employee Details | While Choosing View Option upto Skill tab save buttons are unable to found, After moving to award tab all the save and grid options are enabled, while saving the employee details it showing as exemption occurred message, while saving salary tab it showings are updated successfully message | Additionally added generate letter button, need clarification, unable to generate letter - Others are working
3 | HR Data | Employee Details | State and Salutations are not mandatory, but while editing and saving the employee details it asking as mandatory, after updating also unable to save the record, it showing exemption occurred message | Working
4 | HR Data | Employee Details | Service Position and position status must be disable, but now its open | Working
| HR Data | Employee Details | While trying to insert the employee manually with mandatory details it showing Updation Failed message, unable to insert the employee manully | NEW
| HR Data | Employee Details | Location is not changeable ,now it allow us to change | NEW
| HR Data | Employee Details | Once Employee is resigned, we wont allow to make changes, but it allow us to change | NEW
5 | HR Data | Official | If bank name is given Bank account number and IFSC's are mandatory, but now it saving only bank name without accountnumber and IFSC | Not working
| HR Data | Official | If save the record after choosing the paymode alone, it showing Account Number Already Exists …, but account number empty | NEW
| HR Data | Official | In Paymode dropdown, if we disabled some dropdown option using Global dropdown also, it wont work | NEW
| HR Data | Official | Unable to choose Bank name, Unable to enter bank account number and IFSC Code | NEW
6 | HR Data | Official | In Bank Account number, While updating only Single Digit it asking to update minimum 2 digit (Account number Min and Max length digit verfication not down here | Unable to choose Bank name, Unable to enter bank account number and IFSC Code, So unable to check this case
7 | HR Data | Official | In IFSC Code, While updating only Single Digit it asking to update minimum 2 digit (IFSC Code Must Consists of 11 length Combined with Alpha numeric and first 4 character must be a alphabates - Validation not donw here, please check the validations) | Unable to choose Bank name, Unable to enter bank account number and IFSC Code, So unable to check this case
8 | HR Data | Official | We wont allow the duplicate bank account number for employees, not it allowing to update the same number to muliple employee - Duplicate validation not down here) | Unable to choose Bank name, Unable to enter bank account number and IFSC Code, So unable to check this case
9 | HR Data | Official | WE are unable to allow the user to save the bank account number without bank name, but now it allow us to save (If paymode is neft, we wont allow to save without bank anme, account number and IFSC - Validation not down) | Unable to choose Bank name, Unable to enter bank account number and IFSC Code, So unable to check this case
10 | HR Data | Official | WE are unable to allow the user to save the IFSC without bank name and account number, but now it allow us to save (If paymode is neft, we wont allow to save without bank anme, account number and IFSC - Validation not down) | Unable to choose Bank name, Unable to enter bank account number and IFSC Code, So unable to check this case
11 | HR Data | Official | If the employee is probation status we wont allow the user to update the date in contract exp date and Contract month, but now its allow us to upate | Now it allow us to update date in Contract Exp Date
12 | HR Data | Official | Confirmation date and must be auto calculated, if the probation month is given we need to auto calculate the confirmation date, but now it allow us to update | Now it allow us to update the data in manually, If we delete the probation period it showing the DOJ as confirmation date
13 | HR Data | Official | Contract Exp date and must be auto calculated, if the Contract month is given we need to auto calculate the confirmation date, but now it allow us to update | Now it allow us to update the data in manually, If we delete the contrac period it showing the DOJ as Contract closing date and also allow us to enter probation details
14 | HR Data | Official | Employee DOJ is 01.01.2024, while updating the 31/10/2023 as confirmation date it accepting without any error | Working
15 | HR Data | Official | Employee DOJ is 01.01.2024, while updating the 31/10/2023 as Contract Exp date it accepting without any error | Working
16 | HR Data | Official | Auto user creation configuration not done | Not Done still
17 | HR Data | Official | Notice period column is missing | Working
| HR Data | Official | Unable to save the record | NEW
18 | HR Data | Personal | Relegion - Spelling Mistake - Religion - Correct | Working
19 | HR Data | Personal | Passport Single word not Pass port | Working
20 | HR Data | Personal | Driving License Reg No not Driving Reg no | Working
21 | HR Data | Personal | Driving License Expiry Date not Driving Expiry date | Working
22 | HR Data | Personal | Aadhar number field is missing - We have an mandatory settings code for this - configuration missing | Still not Exist
23 | HR Data | Personal | GP Medicalpolicy CompanyNumber - Column Missing | Still not Exist
24 | HR Data | Personal | GP Medical PolicyAmount - Column Missing | Still not Exist
| HR Data | Personal | In Visa Type dropdown, if we disabled some dropdown option using Global dropdown also, it wont work | NEW
25 | HR Data | Education | unable to save the record, it showing please fill all the mandatory details, even after addition education details in grid | Working
| HR Data | Education | after inserting the family details without DOB, it taking the 01/01/1900 as DOB | NEW
26 | HR Data | Asset | Asset Status showing 3 3 time, Draft -Times, issued 3 time all the status 3 times | Still issue exist
27 | HR Data | Asset | unable to save the record, it showing Asset info updation failed, even after adding the asset details in Grid | Still issue exist
28 | HR Data | Asset | We need to allow the user to save the tab without grid also, now its wont | Still issue exist
29 | HR Data | Skill | We need to allow the user to save the tab without grid also, now its wont | Still issue exist
30 | HR Data | Skill | In Upload file it showing You can upload only one file which should not exceed 5 MB, But now it allow us to pick more files | Still issue exist
31 | HR Data | Skill | Unable to view the already added file | Still issue exist
32 | HR Data | Award | If we add the data in grid and save the award of we deleted the same again and save again it again take the same grid data and saving the deleted record | Working
| HR Data | Award | after inserting the Award details without event date, it taking the 01/01/1900 as event date | NEW
33 | HR Data | Award | If we have 2 grid record, while give save without any changes it showing as 4 data ingrid, if saving again it showing 8 data so on | Working
34 | HR Data | Address | Save and Clear button should be in buttom of the screen, now its in middle screen | Working
35 | HR Data | Address | If we cleared and given as save it again showing the cleared data - unable to clear the saved data | Still issue exist
| HR Data | Statutory | ESI Number is minimum 10 number only, but system asking to enter 17 digit | NEW
| HR Data | Statutory | Unable to save the record without UAN, PF and ESI number, even employee is not eligible | NEW
36 | HR Data | Statutory | PAN number validation not done it asking to enter only minimum of 2 digit, we have some validation for PAN number | Working
37 | HR Data | Statutory | PAN duplicate validation not done, it allow the same data for multiple employees | Working
38 | HR Data | Statutory | In Relation ship Global Dropdown, after making the relationship as inactive also, it showing in dropdown | Working after ctrl+F5 only
39 | HR Data | Statutory | PF number Duplicate validation not done, if we add the same number to another employee we wont allow, now its allow | Working
40 | HR Data | Statutory | UAN number Duplicate validation not done, if we add the same number to another employee we wont allow, now its allow | Working
41 | HR Data | Statutory | ESI number Duplicate validation not done, if we add the same number to another employee we wont allow, now its allow | Still issue exist
42 | HR Data | Statutory | Once Bonus applicable only we need to allow the user to enter bonus starts date now it allow if bonus not applicable also | Still issue exist
43 | HR Data | Statutory | Once Gratuity applicable only we need to allow the user to enter Gratuity starts date now it allow if Gratuity not applicable also | Still issue exist
44 | HR Data | Statutory | After giving Clear and saving statutory tab, employee name also cleared from all the tabs and also from search page | Clear Option is removed so unable to check
45 | HR Data | Nominee | Gender - While adding into grid gender saving as code instead of name | Working
46 | HR Data | Nominee | Unable to save the nomination without DOB it showing nomination updation failed message - but DOB not mandatory | Working
47 | HR Data | Nominee | While adding into grid itself if we add the percentage more that 100 we wont allow to add, but now It allow, if same nominee type is given as 50% and 70% while adding we need to show the error message as PF Nominee (Nominee Type) percentage could not be exceed more than 100% but now its allowing | need to restrict only against the same nominee type, now we cant able to add other nominee type also
48 | HR Data | Nominee | If we cleared and given as save it again showing the cleared data - unable to clear the saved data | Clear Option is removed so unable to check
49 | HR Data | Nominee | If we deleted the grid date and given as save it again showing the deleted data | Working
50 | HR Data | Nominee | If we have 2 grid record, while give save without any changes it showing as 4 data ingrid, if saving again it showing 8 data so on | Working
| HR Data | Nominee | In Relation ship Global Dropdown, after making the relationship as inactive also, it showing in dropdown | Working after ctrl+F5 only
| HR Data | Nominee | In Gender Global Dropdown, after making the relationship as inactive also, it showing in dropdown | Working after ctrl+F5 only
| HR Data | Nominee | In Nominee Code Global Dropdown button is not showing record | NEW
51 | HR Data | Document | We need to allow the user to save the tab without grid also, now its wont it showing exemption occurred message | Working
52 | HR Data | Previous Employeement | We need to allow the user to save the tab without grid also, now its wont | Working
53 | HR Data | Previous Employeement | In Upload file it showing You can upload only one file which should not exceed 5 MB, But now it allow us to pick more files | Still issue exist
54 | HR Data | Previous Employeement | Unable to view the already added file | Still issue exist
55 | HR Data | Employee Details Search page | Delete option not working | Working
56 | HR Data | Employee data | Manual creating asking the state and salutations are mandatory, but these two are not mandatory while upload master upload | Unable to create now
57 | HR Data | Employee data | Last highest code is EIS2050, while itserting manually need to show the code as EIS2051, instead of it showing EIS0051 | Unable to create now
58 | HR Data | Master upload | Manual creating asking the state and salutations are mandatory, but these two are not mandatory while upload master upload | Working
59 | HR Data | Master upload | Paygroup is not mandatory while manual create, but it asking as mandatory while upload | Still issue exist
| HR Data | Master upload | While trying to upload with PAN, PF number, UAN and ESI number it showing updation failed, not uploaded and not showing any error | NEW
60 | HR Data | Master Update | While update employee code and name only mandatory, but system asking Rowno : 2,column name : DateOfJoining : DateOfJoining Cannot Be Empty Rowno : 2,column name : Gender : Gender Cannot Be Empty Rowno : 2,column name : GlobalLocation : GlobalLocation Cannot Be Empty Rowno : 2,column name : PossitionStatus : PossitionStatus Cannot Be Empty Rowno : 2,column name : ServicePosition : ServicePosition Cannot Be Empty Rowno : 2,column name : DOB : DOB Cannot Be Empty Rowno : 2,column name : PayGroup : PayGroup Cannot Be Empty | Still issue exist
61 | HR Data | Master Update | While update paymode as neft bank name, account number and IFSC is mandatory now its not showing in error | IFSC is not asking as mandatory
| HR Data | Master Update | While trying to upload with PAN, PF number, UAN and ESI number it showing updation failed, not uploaded and not showing any error | NEW
| HR Data | Master Update | While uploading Bank account number, account number validation not done | NEW
62 | HR Data | Geo Fencing | Only screen design completed | Still same
| HR Data | In Search | Position status dropdown showing only live details

## H2R_New
S.No | Module | Screen | Remarks | Remarks_New
1 | H2R | Job Offer | Search data showing after 4 to 5 Seconds only | Working
2 | H2R | Job Offer | In Referal dropdown, if we disabled some dropdown option using Global dropdown also, it wont work | Working
3 | H2R | Job Offer | Vacancy Position showing empty | Still issue exist
4 | H2R | Job Offer | In Salutation dropdown, if we disabled some dropdown option using Global dropdown also, it wont work | Working after ctrl+F5 only
5 | H2R | Job Offer | In Gender dropdown, if we disabled some dropdown option using Global dropdown also, it wont work | Working after ctrl+F5 only
6 | H2R | Job Offer | In Service Position Dropdown, if we disabled some dropdown option using Global dropdown also, it wont work | Working after ctrl+F5 only
7 | H2R | Job Offer | In Position status dropdown, if we disabled some dropdown option using Global dropdown also, it wont work | Working after ctrl+F5 only
8 | H2R | Job Offer | In Pay structure dropdown, if we disabled some dropdown option using Global dropdown also, it wont work | Working after ctrl+F5 only
9 | H2R | Job Offer | Unable to generate the letter | Still issue exist
10 | H2R | Job Offer | In Export to excel payelement values are not showing | Report is not clear, showing the main and child table separetly
11 | H2R | Job Offer | Once Joined, we wont allow to make changes, but now we can. | Working
|  | Job Offer | After saved vacancy posted date showing as 01-01-1900 | NEW
|  | Applicant induction | While choosing joined option it showing exemption occurred message, but status changed as joined | NEW
12 | H2R | Applicant induction | Once given has joined user created without Role | Still issue exist
13 | H2R | Applicant induction | Unable to generate the letter | Still issue exist
14 | H2R | Applicant induction | In Export to excel payelement values are not showing | Report is not clear, showing the main and child table separetly
15 | H2R | Applicant induction | Once Joined, we wont allow to make changes, but now we can. | Working
16 | H2R | Applicant induction | Their no structure named as unit (Unit is division) its updated for Faber we need to show our base details, it showing in filter | Working
17 | H2R | Increment | While entrying increment increment details are not showing, unable to enter the increment details | Still issue exist
18 | H2R | Increment | Salary revision date accepting the payroll not processed date also, we are unable to enter the increment for payroll not processed date, here we need to calculcate the arrear from the period | Still issue exist
19 | H2R | Increment | In Transaction status dropdown, if we disabled some dropdown option using Global dropdown also, it wont work | Working after ctrl+F5 only
20 | H2R | Increment | Unable to generate the letter | Still issue exist
21 | H2R | Increment | Once finalized, we wont allow to make changes, but now we can, we can change the status again to draft | Working
22 | H2R | Increment | Their no structure named as mode of business and unit (Unit is division and mode of business is subdepartment) its updated for Faber we need to show our base details, it showing in filter | Still issue exist
23 | H2R | Promotion | While entrying Promotion, role dropdown showin the struture role details, in edit mode it showing the user role details | Now Role structure is not showing, showing only grade
24 | H2R | Promotion | Once finalized, we need to update the new structure values in to employee details table, but now its not updating | Still issue exist
25 | H2R | Promotion | Once finalized, in edit mode it showing only one record in grid other records are not showing | Still issue exist
26 | H2R | Promotion | Unable to find the generate letter button | Unable to generate letter
27 | H2R | Promotion | In Exporting Excel grid details are not showing | Report is not clear, showing the main and child table separetly
28 | H2R | Promotion | Once finalized, we wont allow to make changes, but now we can, we can change the status again to draft | We can enter remarks details
29 | H2R | Promotion | We wont allow the promation data as past date, but now it allow | Working
30 | H2R | Promotion | We wont allow the save without chaning any one of the grid new position, but now it allow us to save | Working
31 | H2R | Promotion | Their no structure named as mode of business and unit (Unit is division and mode of business is subdepartment) its updated for Faber we need to show our base details, it showing in filter | Still issue exist
32 | H2R | Location Transfer | Search data showing after 4 to 5 Seconds only | Working
33 | H2R | Location Transfer | In Transaction status dropdown, if we disabled some dropdown option using Global dropdown also, it wont work | Working after ctrl+F5 only
34 | H2R | Location Transfer | In Exporting Excel it showing grid header, but here not grids available | Still issue exist
35 | H2R | Location Transfer | Once finalized, we need to update the new Loaction values in to employee details table, but now its not updating | Working
36 | H2R | Location Transfer | Once finalized, we wont allow to make changes, but now we can, we can change the status again to draft | Working
37 | H2R | Location Transfer | Unable to find the generate letter button | Still issue exist
38 | H2R | Location Transfer | Their no structure named as mode of business and unit (Unit is division and mode of business is subdepartment) its updated for Faber we need to show our base details, it showing in filter | Still issue exist
39 | H2R | Separation | In Reliving type dropdown, if we disabled some dropdown option using Global dropdown also, it wont work | Working after ctrl+F5 only
40 | H2R | Separation | In Separation type dropdown,no data showing in Global dropdown, but values showing in dropdown | Working after ctrl+F5 only
41 | H2R | Separation | Search data showing after 4 to 5 Seconds only | Working
42 | H2R | Separation | Once separation entry updated as resigned need to update the employee status as resigned, but now no changes in employee position status | Working
43 | H2R | Separation | Once separation entry updated as resigned need to update the user status as inactive, but now no changes in user status | Still issue exist
44 | H2R | Separation | Once Separation entry has been deleted, we need to change the employee position status as old status, but now we are not chaning the status while separation, so we are unable to check this point | Working
45 | H2R | Separation | Reason for Reliving and Reason type field is missing in screen | Now Showing Empty
46 | H2R | Separation | In Report, reliving type showing as reliving name and separation type showing as separation name | Working
47 | H2R | Separation | In Report code showing as wrong name and employee code showing in mid of the report | Working
48 | H2R | Separation | In Report Reason for Reliving and Reason type column showing but not in screen, reason type showing as reliving type | Reason type showing as reliving type
49 | H2R | Separation | On column showing as leave type name, not related with separation | Still issue exist
50 | H2R | Separation | Only acceptance and experience letter buttons are available unable to find the reliving letter button, letter also not generated | Unable to generate letter
51 | H2R | Separation | Their no structure named as mode of business and unit (Unit is division and mode of business is subdepartment) its updated for Faber we need to show our base details, it showing in filter | Still issue exist
52 | H2R | Separation | Separation type filter showing the position status dropdown value | Working
53 | H2R | Intra Transfer | Search data showing after 4 to 5 Seconds only | Working
54 | H2R | Intra Transfer | While Saving Transaction date given as 01/05/2024, but it automatically changed as 02/01/1990 after saving | Working
55 | H2R | Intra Transfer | In Transaction status dropdown, if we disabled some dropdown option using Global dropdown also, it wont work | Working after ctrl+F5 only
| H2R | Intra Transfer | In Grid it showing only Grade value, not showing other structure | NEW
56 | H2R | Intra Transfer | Once finalized, new structure values are removed | In Grid it showing only Grade value, not showing other structure
57 | H2R | Intra Transfer | Once finalized, we need to update the new structure values in to employee details table, but now its removing from intra transfer | In Employee details it updated and also infra screen also old grade updated the new grade
58 | H2R | Intra Transfer | In Export, Grid detail showing blank and also once more additional grid showing which is not related to that report | Grid details not showing
59 | H2R | Intra Transfer | Their no structure named as mode of business and unit (Unit is division and mode of business is subdepartment) its updated for Faber we need to show our base details, it showing in filter | Still issue exist
60 | H2R | CCC Extension | Search data showing after 4 to 5 Seconds only | Working
61 | H2R | CCC Extension | Their no structure named as mode of business and unit (Unit is division and mode of business is subdepartment) its updated for Faber we need to show our base details, it showing in filter | Unit cleared, but mode of business showing same
62 | H2R | CCC Extension | There is no Transfer revision date in CCC exten screen, but showing the filter in this name | Removed from filter
63 | H2R | CCC Extension | While Saving New Revision date given as 01/05/2024, but it automatically changed as 02/01/1990 after saving | Working
64 | H2R | CCC Extension | In Transaction status dropdown, if we disabled some dropdown option using Global dropdown also, it wont work | Working after ctrl+F5 only
65 | H2R | CCC Extension | Probation externed, button not showing any values | Still issue exist
66 | H2R | CCC Extension | Letter generation not working | Still issue exist
67 | H2R | CCC Extension | Once finalized, we need to change the employee position status in Employee db table, not its not changed | Working
68 | H2R | CCC Extension | Once finalized, we cant able to make any changes, but not its allow us to make changes | Working
69 | H2R | CCC Extension | In Exporting Excel it showing grid header, but here not grids available | Report is not clear, showing the main and child table separetly
70 | H2R | CCC Extension | In Report Employee code and Name filter showing 2 times | Working

## Leave_New
S.No | Module | Screen | Remarks | Remarks_New
1 | Leave | Holiday Calender | While choosing date if the date is not in selected period need to show the error as Selected date is not in selected period, please check, but now its not checking the date it in selected period or not | Still issue exist
2 | Leave | Holiday Calender | Search data showing after 4 to 5 Seconds only | Working
3 | Leave | Holiday Planner | Search data showing after 4 to 5 Seconds only | Working
4 | Leave | Holiday Planner | If we save without selecting Holidays need to show the error as Please select Holidays, but now its accepting without selecting holiday also | Working
5 | Leave | Holiday Planner | In Exporting Excel, Unable to see the holiday lists, Holiday list grid is empty | Report is not clear, showing the main and child table separetly
6 | Leave | Holiday Planner | Delete button is not performing, unable to delete | Working
7 | Leave | Holiday Planner | Wont allow the Holiday planner in duplicate name, now its allowing duplicate holiday planner name | Working
8 | Leave | Leave Process | Unable to get the grid data while processing, but downloaded the leave process data in leave process upload screen for the period for May 24 in management payroll, but not showing the data Leave process screen | While choosing it showing exemption occurred message
9 | Leave | Leave Adjustment | Leave type filter need to load only leave filter checked leave types, now it showing all the leave types | Working
10 | Leave | Leave Balance Upload | Leave type need to allow only leave filter checked leave types, now it showing all the leave types | Still issue exist
11 | Leave | Leave Credit Policy | Unable to check the screen, all the dropdowns are empty | Screen not available
12 | Leave | Leave Credit Policy | Screen name is not showing | Screen not available
13 | Leave | Leave Taken Policy | Screen name is not showing | Working
14 | Leave | Leave Taken Policy | In Stoke it showing the payelement name instead of stoke name | Showing Empty
15 | Leave | Leave Taken Policy | Total number of days showing leave taken policy name, unable to enter the day details, once we earsed, leave taken policy name also erased | In Total number of days it allow alphabets instead of Numeric
16 | Leave | Leave Taken Policy | Day Span loading payelement name instead of day span | Showing Empty
17 | Leave | Leave Taken Policy | Custom rule loading payelement name instead of custom rule dropdown | Showing Empty
18 | Leave | Leave Taken Policy | Unable to check the screen, all the dropdowns are incorrect | Unable to check the screen, all the dropdowns are Empty
19 | Leave | Leave Policy | Unable to check the screen, because of leave credit and taken policys are empty | Screen not available
20 | Leave | Leave Policy | We have two leave policy screen, now we have only one | Screen not available

## Payroll_New
S.No | Module | Screen | Remarks | Remarks_New
1 | Payroll | Payelement | Search data showing after 4 to 5 Seconds only | Working
2 | Payroll | Payelement | In element type Global Dropdown, after making the some data's as inactive also, it showing in dropdown | After clicking, its not showing anything showing blank
3 | Payroll | Payelement | In element method Global Dropdown, after making the some data's as inactive also, it showing in dropdown | After clicking, its not showing anything showing blank
4 | Payroll | Payelement | In Benefit Period Global Dropdown, after making the some data's as inactive also, it showing in dropdown | After clicking, its not showing anything showing blank
5 | Payroll | Payelement | In Exporting excel, it showing the grid header 2 times which is not required | Working
6 | Payroll | Payelement | In Payelement type, payelement method and element nature need to show the names, now it showing ID | Working
7 | Payroll | Payelement | In Report Paygroup column not required | Working
8 | Payroll | Payelement | In Report instead of True or false, need to show yes or no for flag details | Working
9 | Payroll | Payelement | Custom1, 2 and 3 are not showing in report | Working
10 | Payroll | Rule bulider | Search data showing after 4 to 5 Seconds only | Working
11 | Payroll | Rule bulider | In Exporting excel, it showing the grid header 2 times which is not required | Total line not required
12 | Payroll | Rule bulider | Exporting Excel report in incorrect order | Still has same issue
13 | Payroll | Rule bulider | In Arrear Maaping, element mapping need to show the names, now it showing ID | Working
14 | Payroll | Rule bulider | Paygroup ID,RuleAreaElementType, Rule type,Extendardsecion,ExtendardRulearea, RulePriorityName columns not required | Working
15 | Payroll | Rule bulider | Round off column showing two times | Working
16 | Payroll | Rule bulider | In Map element Global Dropdown, after making the some data's as inactive also, it showing in dropdown | After clicking, its not showing anything showing blank
17 | Payroll | Rule bulider | In rule type Global Dropdown, after making the some data's as inactive also, it showing in dropdown | After clicking, its not showing anything showing blank
18 | Payroll | Rule bulider | In Round off Global Dropdown, after making the some data's as inactive also, it showing in dropdown | After clicking, its not showing anything showing blank
19 | Payroll | Rule bulider | In Earning And Deduction, Earnings and dedcution column are overlapped | Working
20 | Payroll | Rule bulider | Unable to clear the selected number alone, while choosing clear in number box, it cleared all the rules | Working
21 | Payroll | Rule bulider | If the rule type as direct we wont allow to enter the data in Rule area, now its allowing | Working
22 | Payroll | Statutory Builder | While saving the record it showing updating failed, but entry inserted | Working
23 | Payroll | Statutory Builder | Search data showing after 4 to 5 Seconds only | Working
24 | Payroll | Statutory Builder | In screen Company name Dropdown it showing only current company, but in filter It showing all the companies | Still has same issue
25 | Payroll | Statutory Builder | While inserting I have choosed only Company name, but in edit mode it showing PT_LWF_ComissonerDetails grid with values, if we delete and inserted again, grid details showing 2 times | Working
26 | Payroll | Statutory Builder | Report is not necessary, it showing unwanted columns | Still has same issue
27 | Payroll | PT | In Payroll type Global Dropdown, after making the some data's as inactive also, it showing in dropdown | After clicking, its not showing anything showing blank
28 | Payroll | PT | Unable to find the PT Value grid to check the screen, PT grid details are not available | Working
29 | Payroll | PT | After saving value will be inserted in statutory builder screen, now we are unable to check this point | unable to save, so unable to check this point
| Payroll | PT | Unable to make changes, Save button not available | NEW
30 | Payroll | Payslip Designer | While choosing the screen it showing exemption occurred message | Working
31 | Payroll | Payslip Designer | Master and Payelement fields are not showing to create | Working
32 | Payroll | Payslip Designer | Spelling, Payslip not pay slip in both search page and screen | Still has same issue
33 | Payroll | Payslip Designer | Report is not necessary, it showing unwanted columns | Still has same issue
34 | Payroll | Payslip Designer | We can able to perform save in view mode also | Still has same issue
35 | Payroll | Monthly input | Please let me know the purpose of select all and check boxes | Still has same issue
36 | Payroll | Monthly input | Search data showing after 4 to 5 Seconds only | Working
37 | Payroll | Monthly input | In Transaction status Global Dropdown, after making the some data's as inactive also, it showing in dropdown | After clicking, its not showing anything showing blank
38 | Payroll | Monthly input | In Export to excel it showing only paygroup name period and status, in that status and paygroup showing code instead of name, date format is mismatched, report not required | Report not required
39 | Payroll | Monthly input | We wont allow to delete monthly input once payroll is created against that period and paygroup, now it allow us to delete | Working
40 | Payroll | Monthly input uplaod | while choosing the screen first time all the dropdowns are empty, it takes 4 to 5 sec loading time for dropdown | Working
41 | Payroll | Monthly input uplaod | While downloading template, if we already created the monthly input against the selected period and paygroup, we need to show the already updated data also in downloaded excel, now it showing all the value as 0, if we already done the monthly input for one 5 employee but totally we have 10 employee against that paygroup, we need to download the already created data, while first time only we need to show the fresh data, for 1st time that template is ok, once that is already created, we need to download only already created data not fresh one | Still has same issue
42 | Payroll | Monthly input uplaod | In upload error it showing the one error in multiple time | Still has same issue
| Payroll | Monthly input uplaod | While downloading fresh it showing some values | NEW
| Payroll | Monthly input uplaod | uploading the data for alrady uploaded period, it wont change, it showing the old data only | NEW
43 | Payroll | Payelement Upload | while choosing the screen first time all the dropdowns are empty, it takes 4 to 5 sec loading time for dropdown | Working
44 | Payroll | Payelement Upload | While downloading template, if we already uploaded the salary against the paygroup, we need to show the already updated data also in downloaded excel, now it showing all the value as 0, we need to download the already created data, while first time (New Employee) only we need to show the fresh data, for 1st time that template is ok, once that is already updated, we need to download only already updated data not fresh one | Working
45 | Payroll | Payelement Upload | Date need to show in dd/mm/yyyy format | Working
46 | Payroll | LWF | Unable to find the LWF Value grid to check the screen, LWF grid details are not available | Now Grid showing only employee share, employer share is not showing
47 | Payroll | LWF | After saving value will be inserted in statutory builder screen, now we are unable to check this point | Inserted only value available data, 0 datas are not inserted
48 | Payroll | Paygroup Master | After saving the data unable to view the added data in search page | Working
49 | Payroll | Paygroup Master | In both filter in showing data picker instead of dropdown | Working
50 | Payroll | Paygroup Master | In Exporting Excel, it showing all the company data, Waid restiction not done | Working
51 | Payroll | Paygroup Master | Need to know the Reason of Regular, Settlement and FMS dogle button | Still has same issue
52 | Payroll | Payroll Process | We can able to add multiple record against the same period and paygroup | While additing the payroll process against the same period and paygroup it showing updated successfully message, but not inserted, need to show the record already exist message
53 | Payroll | Payroll Process | Auto PT Deduction is not able to check, due to entry not updated in statutory bulider report | unable to check the details, because, review payroll by employee report is not downloaded, it showing exemption occurred message
54 | Payroll | Payroll Process | Auto LWF Deduction is not able to check, due to entry not updated in statutory bulider report | unable to check the details, because, review payroll by employee report is not downloaded, it showing exemption occurred message
55 | Payroll | Grade Pay FMS | Paygroup is mandatory, now we are able to save without paygroup also, If we save without paygroup it showing inserted successfully message but not showing in grid | After saving it wont showing in grid
56 | Payroll | Grade Pay FMS | If the Monthly input FMS settings code is yes wont allow the user to change the grade in employee details, not grade dropdown is open, in this | Working
57 | Payroll | Grade Pay FMS | We wont Allow the Dupliate grade, not it allows the duplicate grade, we can able to add multiple time | Working
58 | Payroll | Grade Pay FMS | Once Grade name is created, we wont allow the user to make changes in grade name, but now it allow us to make chages | Working
59 | Payroll | Grade Pay FMS | Once Created Grade is mapped with Employee, we wont allow to delete the record, but it allow us to delete | working
60 | Payroll | Monthly input upload FMS | Single Errorlog writing multiple time | Still has same issue
61 | Payroll | Monthly input upload FMS | If we uploaded the data successfully at one time, in monthly input FMS it created two time | Now inserted single time, but paygroup not showing, also unable to check the uploaded data, showing blank
62 | Payroll | Monthly input upload FMS | If we uploaded the file second time, in monthly input FMS it created four times, need to change the already available value but now it inserting multiple time | Now inserted single time, but paygroup not showing, also unable to check the uploaded data, showing blank
63 | Payroll | Month input FMS | In Edit mode we need to check the uploaded value, but now we cant able to check, it showing sorry no data available message | Still has same issue
64 | Payroll | Month input FMS | uploaded the employee with different grade but virtual code is not created | Showing blank unable to check the virtual code created or not
65 | Payroll | Month input FMS | after uploading Paygroup is not showing in monthly input FMS, Paygroup showing blank, even it has mapped in upload option | Still has same issue
66 | Payroll | Month input FMS | We are unable to map the paygroup manually | Still has same issue
67 | Payroll | Month input FMS | Create option is not working, we are unable to find the process option in available | Button missing, unable to create
68 | Payroll | Payroll Process FMS | Unable to check because of paygroup not mapped in monthly input FMS | Still has same issue
69 | Payroll | FMS Data Posting | Unable to check because of paygroup not mapped in monthly input FMS | Still has same issue
70 | Payroll | Single Employee Payroll Process | PostSingleEmpPayrollprocess Updation Failed error showing while process, Message need to change | it showing payroll process not exist error, even it has payroll process value
71 | Payroll | Payroll Settlements | In Employee Code Dropdown, need to show only resigned employee, but now it showing all the employees | Working
72 | Payroll | Payroll Settlements | In Period Dropdown, need to load only monthly period type period now it showing all the periods | Still has same issue
73 | Payroll | Payroll Settlements | In that we need to give only paid days or absorbed days, only one data we need to fill, if we fill only paid days, it asking to update the absorbed days | Still has same issue
74 | Payroll | Payroll Settlements | While inserting Settlement one time values are not showing in screen | Still has same issue
75 | Payroll | Payroll Settlements | While inserting the settlement for live employee it showing PostPayrollsettlement Successfully message but data not showing in Search page | Working
76 | Payroll | Payroll Settlements | While inserting the settlement for resigned employee it showing PostPayrollsettlement Successfully message but data not showing in Search page | Now it showing but we are unable to check the netpay
77 | Payroll | Payroll Settlements | Success message need to change | Working
78 | Payroll | Payroll Settlements | Unable to check filter and report, because of unable to insert the data | Their no structure named as mode of business and filters are not working
| Payroll | Payroll Settlements | Unable to generate settlement payslip, and calculations are not done | NEW
79 | Payroll | Loan Entry | In Screen need to change the date format as dd/mm/yyyy | Working
80 | Payroll | Loan Entry | Loan Effective date need to update now given as month | Still has same issue
81 | Payroll | Loan Entry | Transaction status global dropdown is not working | After clicking, its not showing anything showing blank
82 | Payroll | Loan Entry | After updating the loan Value and EMI, need to calculate the Interest amount, total loan amount, loan per month and out standing amount automatically, now its not working | Columns missing
83 | Payroll | Loan Entry | Unable to save the entry while saving it showing Exception Occurred message | Working
84 | Payroll | Review Grade pay | All the filters are showing as Date picker instead of Dropdown | Working
85 | Payroll | Review Grade pay | In export to PDF, first page showing as blank and Columns are not in order and payelement values also not showing | PDF Removed
86 | Payroll | Review Grade pay | Select Column option is not working if we select one or 2 columns also it downloading all the columns | Working
87 | Payroll | Review Grade pay | In export in excel, Columns are not in order and payelement values also not showing | Still has same issue
88 | Payroll | Review Monthly Input FMS | Status filter dropdown is showing wrong data's | Status filter not working
89 | Payroll | Review Monthly Input FMS | unable to check the export to excel because of no record showing in this screen, even we have FMS monthly input | Working
90 | Payroll | Review Paysheet FMS | All the filters are showing as Date picker instead of Dropdown | Their no structure named as unit (Unit is division) its updated for Faber we need to show our base details, it showing in filter
91 | Payroll | Review Paysheet FMS | unable to check the export to excel because of no record showing in this screen | Still has same issue
92 | Payroll | Review Pay Master | Select Column option is not working if we select one or 2 columns also it downloading all the columns | Working
93 | Payroll | Review Pay Master | In export to PDF, first page showing as blank | Still has same issue
94 | Payroll | Review Pay Master | In both PDF and Excel it showing the Workarea ID instead of name | In Excel working, in PDF still same
95 | Payroll | Review Rule Builder | Select Column option is not working if we select one or 2 columns also it downloading all the columns | Working
96 | Payroll | Review Rule Builder | In export to PDF, first page showing as blank | Still has same issue
97 | Payroll | Review Rule Builder | In both PDF and Excel it showing the Workarea ID instead of name | In Excel working, in PDF still same
98 | Payroll | Review Monthly Input | Select Column is not showing the column names | Still has same issue
99 | Payroll | Review Monthly Input | In search page it totally showing 1275 records but in excel it showing only 50 records | Showing only 7 row, so unable to check
100 | Payroll | Review Monthly Input | In both PDF and Excel it showing the Workarea ID instead of name | PDF Removed and excel its working
101 | Payroll | Review Payroll | Select Column option is not working if we select one or 2 columns also it downloading all the columns | Working
102 | Payroll | Review Payroll | In export to PDF, first page showing as blank | Still has same issue
103 | Payroll | Review Payroll | In both PDF and Excel it showing the Workarea ID instead of name | In Excel working, in PDF still same
104 | Payroll | PF ECR | While choosing PF ECR Application gets logged out automatically | Still has same issue
105 | Payroll | Review Employee PT | Select Column is not showing the column names | Still has same issue
106 | Payroll | Review Employee PT | In export to PDF, first page showing as blank | Still has same issue
107 | Payroll | Review Employee PT | In both PDF and Excel it showing the Workarea ID instead of name | In Excel working, in PDF still same
108 | Payroll | Review_NAPSKAG | unable to check the export to excel because of no record showing in this screen | No Records available

## OPSR_NEW
S.No | Module | Screen | Remarks | Remarks_New
1 | Payroll Reports | Review Payroll by employee | Export PDF showing upto DOB record, not showing Payroll details | It showing no data found message even it has data in payroll process
2 | Payroll Reports | Review Payroll by employee | Select Column option is not working, not showing the column name to select | It showing no data found message even it has data in payroll process
3 | Payroll Reports | Review Payroll by employee | Group by filter is not working | It showing no data found message even it has data in payroll process
4 | Payroll Reports | Payroll Reconcilation | Filter name Unit and mode of business need to be change as per base application | Still has same issue
5 | Payroll Reports | Payroll Reconcilation | Select Column option is not working, not showing the column name to select | Still has same issue
6 | Payroll Reports | Payroll Reconcilation | Export PDF is not required | Removed
7 | Payroll Reports | Payroll Reconcilation | Unable to generate the report due to data not available | Unable to generate the report due to data not available
8 | Payroll Reports | Review Annual Summary | Filter name Unit and mode of business need to be change as per base application | Filter name mode of business need to be change as per base application
9 | Payroll Reports | Review Annual Summary | Select Column option is not working, not showing the column name to select | Still has same issue
10 | Payroll Reports | Review Annual Summary | Export PDF is not required | Removed
11 | Payroll Reports | Review Annual Summary | Group by filter is not working | Unable to generate the report due to data not available
12 | Payroll Reports | Review Annual Summary | In Excel Filter, Paygroup showing ID instead of name | Working
13 | Payroll Reports | Review Annual Summary | In Excel Filter, Employee code showing ID instead of name | Working
14 | Payroll Reports | Review Annual Summary | In Excel Filter, WAID showing ID instead of name | Removed
15 | Payroll Reports | Review Payroll by employee | Filter name Unit and mode of business need to be change as per base application | Filter name mode of business need to be change as per base application
16 | Payroll Reports | Review Payroll by employee | In Excel Filter, Paygroup and Workarea showing ID instead of name | It showing no data found message even it has data in payroll process
17 | Payroll Reports | ESIC ECR | Select Column option is not working, not showing the column name to select | Still has same issue
18 | Payroll Reports | ESIC ECR | Export PDF is not required | Removed
19 | Payroll Reports | ESIC ECR | Excel not downloaded for already payroll processed month | Still has same issue
20 | Payroll Reports | ESIC ECR | PDF not required, instead of PDF Required CSV format | PDF Removed, but CSV missing
21 | Payroll Reports | Dynamic Payslip | Select Column option is not working, not showing the column name to select | Removed
22 | Payroll Reports | Dynamic Payslip | Export PDF is not required | Working
23 | Payroll Reports | Dynamic Payslip | Export Excel is not required | Removed
24 | Payroll Reports | Dynamic Payslip | While choosing Print Payslip not downloaded | It showing no data found message even it has data in payroll process
25 | Payroll Reports | Dynamic Payslip | Send email option missing | Still has same issue
26 | Payroll Reports | Dynamic Payslip | Option type and dropdown type - Filter Requirements Please? | Still has same issue
27 | Payroll Reports | Dynamic Payslip | Filter name Unit need to be change as per base application | Working
28 | Payroll Reports | Review PF ECR Revised | Select Column option is not working, not showing the column name to select | Still has same issue
29 | Payroll Reports | Review PF ECR Revised | Export PDF is not required | Removed
30 | Payroll Reports | Review PF ECR Revised | Excel not downloaded for already payroll processed month | Still has same issue
31 | Payroll Reports | Review PF ECR Revised | PDF not required, instead of PDF Required CSV format | PDF Removed, but CSV missing
32 | Payroll Reports | Review PF ECR Revised | Print Option not required | Removed
33 | Payroll Reports | Review PF ECR Revised | Filter name Unit and mode of business need to be change as per base application | Filter name mode of business need to be change as per base application
34 | Payroll Reports | Gratuity Calculation | Filter name Unit and mode of business need to be change as per base application | Unable to find the report to check
35 | Payroll Reports | Gratuity Calculation | Service Position dropdown empty | Unable to find the report to check
36 | Payroll Reports | Gratuity Calculation | While choosing it showing Gratuity Calculation is not done properly. Please check | Unable to find the report to check
37 | Payroll Reports | Gratuity Calculation | Select Column option is not working, not showing the column name to select | Unable to find the report to check
38 | Payroll Reports | Gratuity Calculation | Export PDF is not required | Unable to find the report to check
39 | Payroll Reports | Gratuity Calculation | Print Option not required | Unable to find the report to check
40 | Payroll Reports | Gratuity Calculation | Unable to generate the report due to data not available | Unable to find the report to check
41 | Payroll Reports | Review PF UAN Generation | While choosing the screen, application gets logged out automatically | Working
| Payroll Reports | Review PF UAN Generation | Filter name Unit and mode of business need to be change as per base application | New
| Payroll Reports | Review PF UAN Generation | Select Column option is not working, not showing the column name to select | New
| Payroll Reports | Review PF UAN Generation | It showing no data found message even it has data in payroll process | New
42 | Payroll Reports | Monthly Pay sheet | Configuration not done, unable to download | It showing no data found message even it has data in payroll process
43 | Payroll Reports | Monthly Pay sheet | Filter name Unit and mode of business need to be change as per base application | Filter name mode of business need to be change as per base application
44 | Payroll Reports | Monthly Pay sheet | Service Position dropdown empty | Working
45 | Payroll Reports | Monthly Pay sheet | Select Column option is not working, not showing the column name to select | Still has same issue
46 | Payroll Reports | Monthly Pay sheet | Export PDF is not required | Removed
47 | Payroll Reports | Review Professional Tax | Select Column option is not working, not showing the column name to select | Still has same issue
48 | Payroll Reports | Review Professional Tax | Export PDF is not required | Removed
49 | Payroll Reports | Review Loan Balance DRA | Configuration not done, unable to download | Unable to find the report to check
50 | Payroll Reports | Review Loan Balance DRA | Export PDF is not required | Unable to find the report to check
51 | Payroll Reports | Review Loan Balance DRA | Print Option not required | Unable to find the report to check
52 | Payroll Reports | Review Loan Balance DRA | Select Column option is not working, not showing the column name to select | Unable to find the report to check
53 | Payroll Reports | Gratuity Report | Export PDF is not required | Unable to find the report to check
54 | Payroll Reports | Gratuity Report | Employee Name Filter not working | Unable to find the report to check
55 | Payroll Reports | Gratuity Report | Select Column option is not working, not showing the column name to select | Unable to find the report to check
56 | Payroll Reports | Gratuity Report | Report Details not clear, please explain | Unable to find the report to check
57 | Payroll Reports | Review Salary Reconciliation | Select Column option is not working, not showing the column name to select | Still has same issue
58 | Payroll Reports | Review Salary Reconciliation | Export PDF is not required | Removed
59 | Payroll Reports | Review Salary Reconciliation | Unable to generate the report due to data not available | Unable to generate the report due to data not available

## Sheet2
PAN | CGAPP4444F
PF | TNMAS1423344000000003
UAN | 101657797433
ESI | 51268714643333300